## Gantt Chart
All
Digital Curation of the British Library Drama Dataset | [41 empty] | Liangyu
Xinran
PROJECT BACKGROUND |  | PROJECT MANAGER, MEMBERS |  |  | START DATE | END DATE | [14 empty] | PROJECT DURATION | [15 empty] | COLOR |  |  |  |  | Chahna
Execution of an 8-week digital curation lifecycle for the British Library Drama Dataset. |  | Liangyu Gan, Xinran Liu, Chahna Paresh Ahuja |  |  | 2025-10-12 | 2025-12-07 | <--Enter date of Sunday of first week. | [13 empty] | 56 DAYS | [20 empty] | MILESTONE
Real start date is 2025-10-13
WBS | TASK NAME | START DATE | FINISH DATE | DURATION in days | PERCENTAGE COMPLETE | OWNER | 2025-10-12 | [6 empty] | 2025-10-19 | [6 empty] | 2025-10-26 | [6 empty] | 2025-11-02 | [6 empty] | 2025-11-09 | [6 empty] | 2025-11-16 | [6 empty] | 2025-11-23 | [6 empty] | 2025-11-30 | [6 empty] | 2025-12-07
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Initiation and Protocol Definition | 2025-10-13 | 2025-10-26 | 14 | 100% | Team
1.1 | Project Kick-off & Sheet Assessment | 2025-10-13 | 2025-10-15 | 3 | 100% | Liangyu | bar: 2025-10-12 M to 2025-10-12 W
1.2 | Define "Cleaning Protocol" | 2025-10-16 | 2025-10-26 | 11 | 100% | Chahna | bar: 2025-10-12 R to 2025-10-26 Su
1.3 | Environment Setup (GitHub/Notion/OneDrive) | 2025-10-20 | 2025-10-21 | 2 | 100% | Xinran | bar: 2025-10-19 Su to 2025-10-19 M
MILESTONE 1 | Protocol Freeze | 2025-10-26 | 2025-10-26 | 1 | 100% | Team | bar: 2025-10-26 Su
2 | Distributed Data Cleaning | 2025-10-27 | 2025-11-23 | 28 | 100% | Team
2.1
2.2
2.3
2.4
2.5
2.6
2.7
2.8
2.9
2.10.
2.1 | Author Normalization (Parallel) | 2025-10-27 | 2025-11-02 | 7 | 100% | All | bar: 2025-10-26 M to 2025-11-02 Su
2.2 | Title & Metadata Cleaning (Parallel) | 2025-11-03 | 2025-11-13 | 11 | 100% | All | bar: 2025-11-02 M to 2025-11-09 R
2.3 | Imprint Standardization (Parallel) | 2025-11-14 | 2025-11-20 | 7 | 100% | All | bar: 2025-11-09 F to 2025-11-16 R
2.4 | Wikidata Coordination and Finalisation (Parallel) | 2025-11-20 | 2025-11-23 | 4 | 100% | All | bar: 2025-11-16 R to 2025-11-23 Su
MILESTONE 2 | Completion of Distributed Data Cleaning | 2025-11-23 | 2025-11-23 | 1 | 100% | Team | bar: 2025-11-23 Su
3 | Quality Assurance and Integration | 2025-11-24 | 2025-12-01 | 8 | 100% | Team
3.1
3.2
3.3
3.4
3.5
3.6
3.7
3.8
3.9
3.10.
3.1 | Peer Review (Dataset Swap & Data Sampling) | 2025-11-24 | 2025-11-27 | 4 | 100% | Xinran | bar: 2025-11-23 M to 2025-11-23 R
3.2 | Schema Alignment & Merge | 2025-11-28 | 2025-12-01 | 4 | 100% | Chahna | bar: 2025-11-23 F to 2025-11-30 M
MILESTONE 3 | Integration Sign-off | 2025-12-01 | 2025-12-01 | 1 | 100% | Team | bar: 2025-11-30 M
4 | Documentation and Closure | 2025-12-01 | 2025-12-07 | 7 | 100% | Team
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10.
4.1 | Export JSON History & GREL | 2025-12-01 | 2025-12-04 | 4 | 100% | All | bar: 2025-11-30 M to 2025-11-30 R
4.2 | Final Report Compilation | 2025-12-02 | 2025-12-06 | 5 | 100% | Liangyu | bar: 2025-11-30 T to 2025-11-30 Sa
MILESTONE 4 | Final Delivery | 2025-12-07 | 2025-12-07 | 1 | 100% | Team | bar: 2025-12-07 Su
17.1
17.2
17.3
17.4
17.5
17.6
17.7
17.8
17.9
17.10.